## Journal
Task ID | Status | Estimate | Actual | Feature ID | Description
Date: | 2020-06-06 |  |  |  | Hours Worked: 7.25
1 | In Progress | 1.5 | 0.75 | 18 | Create Ability class
6 | Completed | 1.5 | 0.5 | 32 | Create entity class
7 | Completed | 0.25 | 0.25 | 33 | allow entities to hold up to 4 abilities
10 | Completed | 2.5 | 1.5 | 1 | Create a player character class that inherits entity class
11 | Completed | 1.5 | 0.5 | 2 | Implement ability to control player character via mouse
12 | Completed | 1 | 1 | 2 | Implement ability for player to use abilities
30 | Completed | 1 | 0.75 | 46 | Create an in game ability bar Ui that shows cooldowns for all equipped abilities
56 | Completed | 1 | 2 | 3, 16 | Implement Blink Ability type
Date: | 2020-06-15 |  |  |  | Hours Worked: 9
1 | In Progress | 1.5 | 0.75 | 18 | Create Ability class
2 | Completed | 0.5 | 1.75 | 16 | Implement an XML format to create abilities
5 | Completed | 0.75 | 0.75 | 18 | Create projectile class that is used by abilities
17 | Completed | 1 | 0.75 | 31 | Create an enemy class that inherits from entity
28 | Completed | 0.5 | 0.75 | 45 | Create an in game player health bar UI element
29 | Completed | 0.5 | 0.25 | 48 | Create an in game enemy health bar UI element
57 | Completed | 1 | 1 | 3, 16 | Implement Buff Ability type
60 | Completed | 1 | 1 | 0 | Give the player the ability to attack the enemies (basic attack)
61 | Completed | 1.5 | 2 | 16 | Create a method to create abilities from definitions

## Sprints
Task ID | Status | Estimate | Actual | Feature ID | Description
Sprint 1 | Start Date: | 2020-06-02 | End Date: | 2020-06-15 | Total Hours Completed: 16.25
[6 empty] | Deep Learning: | The issue that I had over the course of this milestone was finding the motivation and time to sit down and work on the project. As the deadline approached I got more on the screen it felt easier to want to work on it. Moving forward it will be important to time manage better. Another thing that I found to be an issue was my task planning. When I did my initial task planning I forgot about a lot of things and definitely overscoped the project. Moving forward at the start of the next milestone I am going to take a look at the features list and milestones to reassess what it is I want to accomplish for each. Upon completing the reassessment I will be able to fully plan out the next sprint.
1 | Completed | 1.5 | 1.5 | 18 | Create Ability class
2 | Completed | 0.5 | 1.75 | 16 | Implement an XML format to create abilities
3 | Not Started | 1 | 0 | 19 | Create Item class
4 | Not Started | 0.5 | 0 | 22 | Implement an XML format to create items
5 | Completed | 0.75 | 0.75 | 18 | Create projectile class that is used by abilities
6 | Completed | 1.5 | 0.5 | 32 | Create entity class
7 | Completed | 0.25 | 0.25 | 33 | allow entities to hold up to 4 abilities
8 | Not Started | 0.25 | 0 | 34 | Allow entities to hold an "infinite" number of items
9 | Not Started | 0.5 | 0 | 35 | store number of item type { [1,Axe], [1,Arrow], [2,Sword] }
10 | Completed | 2.5 | 1.5 | 1 | Create a player character class that inherits entity class
11 | Completed | 1.5 | 0.5 | 2 | Implement ability to control player character via mouse
12 | Completed | 1 | 1 | 2 | Implement ability for player to use abilities
13 | Not Started | 1 | 0 | 7 | Implement dodge dash
14 | Not Started | 1 | 0 | 20 | Implement item stats that effect the entity if held
15 | Not Started | 1 | 0 | 21 | Implement item actives
16 | Not Started | 1 | 0 | 21 | Implement the ability for the player to use equipped item actives
17 | Completed | 1 | 0.75 | 31 | Create an enemy class that inherits from entity
28 | Completed | 0.5 | 0.75 | 45 | Create an in game player health bar UI element
29 | Completed | 0.5 | 0.25 | 48 | Create an in game enemy health bar UI element
30 | Completed | 1 | 0.75 | 46 | Create an in game ability bar Ui that shows cooldowns for all equipped abilities
56 | Completed | 1 | 2 | 3, 16 | Implement Blink Ability type
57 | Completed | 1 | 1 | 3, 16 | Implement Buff Ability type
60 | Completed | 1 | 1 | 0 | Give the player the ability to attack the enemies (basic attack)
61 | Completed | 1.5 | 2 | 16 | Create a method to create abilities from definitions
Sprint 2 | Start Date: | 2020-06-16 | End Date: | 2020-06-30 | Total Hours Completed: 0
63 | Not Started | 1 | 0 | - | Reevaluate Milestones and Features
62 | Not Started | 1 | 0 | - | Sprint 2 Planning

## Backlog
Task ID | Status | Estimate | Actual | Feature ID | Description
1 | Completed | 1.5 | 1.5 | 18 | Create Ability class
2 | Completed | 0.5 | 1.75 | 16 | Implement an XML format to create abilities
3 | Not Started | 1 |  | 19 | Create Item class
4 | Not Started | 0.5 |  | 22 | Implement an XML format to create items
5 | Completed | 0.75 | 0.75 | 18 | Create projectile class that is used by abilities
6 | Completed | 1.5 | 0.5 | 32 | Create entity class
7 | Completed | 0.25 | 0.25 | 33 | allow entities to hold up to 4 abilities
8 | Not Started | 0.25 |  | 34 | Allow entities to hold an "infinite" number of items
9 | Not Started | 0.5 |  | 35 | store number of item type { [1,Axe], [1,Arrow], [2,Sword] }
10 | Completed | 2.5 | 1.5 | 1 | Create a player character class that inherits entity class
11 | Completed | 1.5 | 0.5 | 2 | Implement ability to control player character via mouse
12 | Completed | 1 | 1 | 2 | Implement ability for player to use abilities
13 | Not Started | 1 |  | 7 | Implement dodge dash
14 | Not Started | 1 |  | 20 | Implement item stats that effect the entity if held
15 | Not Started | 1 |  | 21 | Implement item actives
16 | Not Started | 1 |  | 21 | Implement the ability for the player to use equipped item actives
17 | Completed | 1 | 0.75 | 31 | Create an enemy class that inherits from entity
18 | Not Started | 2 |  | 8 | Create preset stat sets that modify the player character's base stats
19 | Not Started | 0.5 |  | 9 | Have stat sets hold experience
20 | Not Started | 0.5 |  | 9 | Assign number of skill points for stat set based on experience
21 | Not Started | 1 |  | 11,15 | Give each stat set a unique ability that utilizes its modified stats
22 | Not Started | 1.5 |  | 14 | Implement a way to updgrade abilities using the skill points from the selected stat set
23 | Not Started | 1 |  | 10 | Implement the ability to level up a stat set by assigning skill points
24 | Not Started | 1.5 |  | 3 | Create a menu that allows the player to choose 3 abilites from a catalog of abilities
25 | Not Started | 0.5 |  | 4 | Create a menu that allows the player to choose which stat set they want to use
26 | Not Started | 0.5 |  | 4 | Display player stats with current loadout
27 | Not Started | 1 |  | 5 | Create a menu to assign skill points to abilities and/or stats
28 | Completed | 0.5 | 0.75 | 45 | Create an in game player health bar UI element
29 | Completed | 0.5 | 0.25 | 48 | Create an in game enemy health bar UI element
30 | Completed | 1 | 0.75 | 46 | Create an in game ability bar Ui that shows cooldowns for all equipped abilities
31 | Not Started | 2 |  | 6 | Create an in game Item inventory UI to select which items are in the active slots
32 | Not Started | 0.75 |  | 47 | Create an in game Item UI to show item active cooldowns
33 | Not Started | 1 |  | 29 | Create quick ranged weak enemy type
34 | Not Started | 1 |  | 29 | Create slow ranged strong enemy type
35 | Not Started | 1 |  | 29 | Create quick melee weak enemy type
36 | Not Started | 1 |  | 29 | Create slow melee strong enemy type
37 | Not Started | 1.5 |  | 30 | Implement simple AI for enemy to move and attack the player
38 | Not Started | 2 |  | 23 | Implement tile based room generation
39 | Not Started | 2 |  | 24 | Implement room generation based on png files
40 | Not Started | 1.5 |  | 25 | Generate floors from randomly selected rooms connected via generated hallways
41 | Not Started | 0.5 |  | 26 | Ensure that each floor has an entrance room that doesnt have enemies
42 | Not Started | 0.5 |  | 28 | Ensure that each floor has an exit room free of enemies
43 | Not Started | 1 |  | 38 | he exit room will have 3 items that the player can choose from before progressing
44 | Not Started | 1 |  | 38 | Implement the ability for the player to pick up items by running over them
45 | Not Started | 1 |  | 36 | Implement an entrance and exit functionality for the player to travel from floor to floor
46 | Not Started | 1 |  | 36 | Implement functionality for the player to return to the main menu upon losing all of their health
47 | Not Started | 1 |  | 39 | Increase enemy stats for every level
48 | Not Started | 1 |  | 40 | Increase number of enemies per room every 10 levels
49 | Not Started | 2 |  | 41 | Increase number of rooms per floor every 5 levels
50 | Not Started | 2 |  | 13 | Every 10 levels the player will unlock a new ability from a tier based system (tier = level/10)
51 | Not Started | 1.5 |  | 37 | Write save state to XML (save unlocked abilities and stat set EXP)
52 | Not Started | 1 |  | 37 | Read game save state from XML
53 | Not Started | 2 |  | - | Implement enemies that use abilities
54 | Not Started | 10 |  | - | Polish
55 | Not Started | 10 |  | - | Bug Fixing
56 | Completed | 1 | 2 | 3, 16 | Implement Blink Ability type
57 | Completed | 1 | 1 | 3, 16 | Implement Buff Ability type
58 | Not Started | 1 |  | 3, 16 | Implement Projectile Ability type
59 | Not Started | 1 |  | 3, 16 | Implement targeted ability type
60 | Completed | 1 | 1 |  | Give the player the ability to attack the enemies (basic attack)
61 | Completed | 1.5 | 2 | 16 | Create a method to create abilities from definitions
62 | Not Started | 1 |  | - | Sprint 2 Planning
63 | Not Started | 1 |  | - | Reevaluate Milestones and Features
Totals
|  | Estimated Hours | 86.5
|  | Actual Hours | 16.25