## Milestones
Milestone 1
Player Character | Player controlled character the inherits from entity
Player Character | Can use 4 abilities via key bindings that are chosen from a selection
Player Character | Can dash using 'Spacebar'
Abilities | Abilites are read in through an XML format
Abilities | are a resource that is gained and kept from run to run
Items | are a resource that is gained through a run
Items | An item will uniquely boost an entity's stats
Items | Each item has a unique active ability
Items | Items are created from an XML document
Enemies | Inherited from entity class
Entity | is a base class for Enemies and Player character that holds stats, abilities, and Items
Entity | Can have up to 4 abilities
Entity | Can store an "infinite" amount of items
Entity | Same Items stack and only give one active
Updated Milestone 2
Graphics | Determine direction to go with visuals
Graphics | Generate Map from sprite sheet
Graphics | Animate Player Character
Graphics | Draw Player Character as Sprite
Graphics | Draw Map with tile
Graphics | Generate Map fom png
Gameplay | Spawn player on map at specified location
Updated Milestone 3
Items | Generate Items from XML
Items | Item class
Player Character | Can pick up dropped Items
Enemies | Chance to drop item on death
Enemies | Behavior to attack player
Gameplay | Pathing on map for player and enemy
Audio | Add SFX and BGM
UI | Menu flows are established
UI/Audio | Control Sound volumes from menu
UI | Create buttons that the player can interact with and change the state of the game

## Sprints
Task ID | Status | Estimate | Actual | Feature ID | Description
Sprint 1 | Start Date: | 2020-06-02 | End Date: | 2020-06-15 | Total Hours Completed: 18.5
[6 empty] | Deep Learning: | The issue that I had over the course of this milestone was finding the motivation and time to sit down and work on the project. As the deadline approached I got more on the screen it felt easier to want to work on it. Moving forward it will be important to time manage better. Another thing that I found to be an issue was my task planning. When I did my initial task planning I forgot about a lot of things and definitely overscoped the project. Moving forward at the start of the next milestone I am going to take a look at the features list and milestones to reassess what it is I want to accomplish for each. Upon completing the reassessment I will be able to fully plan out the next sprint.
1 | Completed | 1.5 | 1.5 | 18 | Create Ability class
2 | Completed | 0.5 | 1.75 | 16 | Implement an XML format to create abilities
3 | Completed | 1 | 1 | 19 | Create Item class
4 | Completed | 0.5 | 0.25 | 22 | Implement an XML format to create items
5 | Completed | 0.75 | 0.75 | 18 | Create projectile class that is used by abilities
6 | Completed | 1.5 | 0.5 | 32 | Create entity class
7 | Completed | 0.25 | 0.25 | 33 | allow entities to hold up to 4 abilities
8 | Completed | 0.25 | 0.25 | 34 | Allow entities to hold an "infinite" number of items
9 | Completed | 0.5 | 0.5 | 35 | store number of item type { [1,Axe], [1,Arrow], [2,Sword] }
10 | Completed | 2.5 | 1.5 | 1 | Create a player character class that inherits entity class
11 | Completed | 1.5 | 0.5 | 2 | Implement ability to control player character via mouse
12 | Completed | 1 | 1 | 2 | Implement ability for player to use abilities
13 | Deleted | 1 | 0 | 7 | Implement dodge dash
14 | Completed | 1 | 0.25 | 20 | Implement item stats that effect the entity if held
15 | Deleted | 1 | 0 | 21 | Implement item actives
16 | Deleted | 1 | 0 | 21 | Implement the ability for the player to use equipped item actives
17 | Completed | 1 | 0.75 | 31 | Create an enemy class that inherits from entity
28 | Completed | 0.5 | 0.75 | 45 | Create an in game player health bar UI element
29 | Completed | 0.5 | 0.25 | 48 | Create an in game enemy health bar UI element
30 | Completed | 1 | 0.75 | 46 | Create an in game ability bar Ui that shows cooldowns for all equipped abilities
56 | Completed | 1 | 2 | 3, 16 | Implement Blink Ability type
57 | Completed | 1 | 1 | 3, 16 | Implement Buff Ability type
60 | Completed | 1 | 1 | 0 | Give the player the ability to attack the enemies (basic attack)
61 | Completed | 1.5 | 2 | 16 | Create a method to create abilities from definitions
Sprint 2 | Start Date: | 2020-06-16 | End Date: | 2020-06-29 | Total Hours Completed: 21.75
[6 empty] | Deep Learning: | Having a plan going into a sprint is very important to creating motivation for doing work. Without a clear goal I found it hard to find motivation to do work. Once I planned out some of my goals/tasks I found it easier to work on things and I started to want to add different features. More thorough time tracking throughout the sprint will be better for accurate time estimate and completion comparisons
63 | Completed | 1 | 1 | - | Reevaluate Milestones and Features
62 | Completed | 1 | 1 | - | Sprint 2 Planning
39 | Completed | 2 | 1.5 | 24 | Implement room generation based on png files
45 | Completed | 1 | 3.75 | 36 | Implement an entrance and exit functionality for the player to travel from floor to floor
64 | Completed | 1 | 0.5 | - | Explore posibilities of vector art
65 | Completed | 1 | 1.5 | - | Explore posibilities of using sprite art
66 | Completed | 1 | 2 | - | Get sprites to use in game
67 | Completed | 0.5 | 0.5 | - | Create World class to manage maps
68 | Completed | 0.5 | 0.5 | - | Create Map Class to hold tiled map
69 | Completed | 0.5 | 0.5 | - | Create tile struct to hold tile definitions
70 | Completed | 1 | 0.75 | - | Create tile definitions read in from XML
71 | Completed | 0.5 | 0.25 | - | Update game management to to World->Map->Entites
72 | Completed | 0.75 | 0.75 | - | Draw Tiles on screen with test texture
73 | Completed | 0.75 | 0.5 | - | Draw Tiles on screen with tile def textures
74 | Completed | 0.25 | 0.25 | - | Create a debugDraw button
76 | Deleted | 2 | 0 | - | Add Simple Physics to map to not allow player to move through solid tiles
78 | Completed | 0.5 | 0.5 | - | Update cursor logic to exist withing a Cursor class
79 | Completed | 0.5 | 0.25 | - | Add different states to cursor
80 | Completed | 0.5 | 0.5 | - | Update Cursor logic to allow easier modification
81 | Completed | 0.5 | 0.5 | - | Update Player logic to allow for easier modification
82 | Completed | 2 | 1 | - | Update entities to render sprites
75 | Completed | 0 | 0.75 | - | Debug existing SpriteSheet class
77 | Completed | 0 | 0.5 | - | Create Cursor SpriteSheet
83 | Completed | 0 | 1.5 | - | Animate Player actions
84 | Completed | 0 | 1 | - | Find an effective way to use external sprite sheets not in out typical format
Sprint 3 | Start Date: | 2020-06-30 | End Date: | 2020-07-13 | Total Hours Completed: 12.5
3 | Completed | 1 | 1 | 19 | Create Item class
4 | Completed | 0.5 | 0.25 | 22 | Implement an XML format to create items
8 | Completed | 0.25 | 0.25 | 34 | Allow entities to hold an "infinite" number of items
9 | Completed | 0.5 | 0.5 | 35 | store number of item type { [1,Axe], [1,Arrow], [2,Sword] }
14 | Completed | 1 | 0.25 | 20 | Implement item stats that effect the entity if held
24 | Completed | 1.5 | 2 | 3 | Create a menu that allows the player to choose 4 abilites from a catalog of abilities
33 | Not Started | 1 | 0 | 29 | Create quick ranged weak enemy type
35 | Not Started | 1 | 0 | 29 | Create quick melee weak enemy type
44 | Not Started | 1 | 0 | 38 | Implement the ability for the player to pick up items by running over them
45 | Completed | 0.25 | 3 | 36 | Implement an entrance and exit functionality for the player to travel from floor to floor
46 | Not Started | 1 | 0 | 36 | Implement functionality for the player to return to the main menu upon losing all of their health
47 | Not Started | 1 | 0 | 39 | Increase enemy stats for every level
51 | Not Started | 1.5 | 0 | 37 | Write save state to XML (save unlocked abilities and stat set EXP)
52 | Not Started | 1 | 0 | 37 | Read game save state from XML
58 | Not Started | 1 | 0 | 3, 16 | Implement Projectile Ability type
59 | Not Started | 1 | 0 | 3, 16 | Implement targeted ability type
86 | Completed | 1 | 1 | - | Add attack move cursor state
87 | Completed | 2 | 1.5 | - | Add player attack move state
88 | Not Started | 1.5 | 0 | - | Add a raycast for line of sight logic
89 | Not Started | 3 | 0 | - | Add Map::PathFromLocationToPoint
90 | Not Started | 2 | 0 | - | Get Audio assets for: BGM, PlayerAttack, EnemyAttack, pick up Item
91 | Not Started | 1.5 | 0 | - | Implement playing audio on actions
92 | Completed | 1 | 1 | - | Creat UI button for menus
93 | In Progress | 1.5 | 0.5 | - | Create Game management of states MENU->PLAYING->LOSE->MENU
94 | Completed | 1.5 | 1 | - | Create main menu
95 | Not Started | 1.5 | 0 | - | Create pause menu
96 | Not Started | 1 | 0 | - | Add SFX volume control to menus
97 | Not Started | 1 | 0 | - | Add BGM volume control to menus
98 | Completed | 0 | 0.25 | - | Add Ability key to ability UI box

## Journal
Task ID | Status | Estimate | Actual | Feature ID | Description
Date: | 2020-06-06 |  |  |  | Hours Worked: 7.25
1 | In Progress | 1.5 | 0.75 | 18 | Create Ability class
6 | Completed | 1.5 | 0.5 | 32 | Create entity class
7 | Completed | 0.25 | 0.25 | 33 | allow entities to hold up to 4 abilities
10 | Completed | 2.5 | 1.5 | 1 | Create a player character class that inherits entity class
11 | Completed | 1.5 | 0.5 | 2 | Implement ability to control player character via mouse
12 | Completed | 1 | 1 | 2 | Implement ability for player to use abilities
30 | Completed | 1 | 0.75 | 46 | Create an in game ability bar Ui that shows cooldowns for all equipped abilities
56 | Completed | 1 | 2 | 3, 16 | Implement Blink Ability type
Date: | 2020-06-15 |  |  |  | Hours Worked: 9
1 | In Progress | 1.5 | 0.75 | 18 | Create Ability class
2 | Completed | 0.5 | 1.75 | 16 | Implement an XML format to create abilities
5 | Completed | 0.75 | 0.75 | 18 | Create projectile class that is used by abilities
17 | Completed | 1 | 0.75 | 31 | Create an enemy class that inherits from entity
28 | Completed | 0.5 | 0.75 | 45 | Create an in game player health bar UI element
29 | Completed | 0.5 | 0.25 | 48 | Create an in game enemy health bar UI element
57 | Completed | 1 | 1 | 3, 16 | Implement Buff Ability type
60 | Completed | 1 | 1 | 0 | Give the player the ability to attack the enemies (basic attack)
61 | Completed | 1.5 | 2 | 16 | Create a method to create abilities from definitions
Date: | 2020-06-23 |  |  |  | Hours Worked: 9.5
63 | In Progress | 1 | 0.5 | - | Reevaluate Milestones and Features
62 | In Progress | 1 | 0.5 | - | Sprint 2 Planning
39 | In Progress | 2 | 1 | 24 | Implement room generation based on png files
64 | Completed | 1 | 0.5 | - | Explore posibilities of vector art
65 | Completed | 1 | 1.5 | - | Explore posibilities of using sprite art
66 | In Progress | 1 | 1 | - | Get sprites to use in game
67 | Completed | 0.5 | 0.5 | - | Create World class to manage maps
68 | Completed | 0.5 | 0.5 | - | Create Map Class to hold tiled map
69 | Completed | 0.5 | 0.5 | - | Create tile struct to hold tile definitions
70 | Completed | 1 | 0.75 | - | Create tile definitions read in from XML
72 | Completed | 0.75 | 0.75 | - | Draw Tiles on screen with test texture
73 | Completed | 0.75 | 0.5 | - | Draw Tiles on screen with tile def textures
74 | Completed | 0.25 | 0.25 | - | Create a debugDraw button
75 | Completed | 0 | 0.75 | - | Debug existing SpriteSheet class
Date: | 2020-06-29 |  |  |  | Hours Worked: 12.25
63 | Completed | 1 | 0.5 | - | Reevaluate Milestones and Features
62 | Completed | 1 | 0.5 | - | Sprint 2 Planning
39 | Completed | 2 | 0.5 | 24 | Implement room generation based on png files
45 | In Progress | 1 | 3.75 | 36 | Implement an entrance and exit functionality for the player to travel from floor to floor
66 | Completed | 1 | 1 | - | Get sprites to use in game
71 | Completed | 0.5 | 0.25 | - | Update game management to to World->Map->Entites
78 | Completed | 0.5 | 0.5 | - | Update cursor logic to exist withing a Cursor class
79 | Completed | 0.5 | 0.25 | - | Add different states to cursor
80 | Completed | 0.5 | 0.5 | - | Update Cursor logic to allow easier modification
81 | Completed | 0.5 | 0.5 | - | Update Player logic to allow for easier modification
82 | Completed | 2 | 1 | - | Update entities to render sprites
77 | Completed | 0 | 0.5 | - | Create Cursor SpriteSheet
83 | Completed | 0 | 1.5 | - | Animate Player actions
84 | Completed | 0 | 1 | - | Find an effective way to use external sprite sheets not in out typical format
Date: | 2020-07-06 |  |  |  | Hours Worked: 4
3 | Completed | 1 | 1 | 19 | Create Item class
4 | Completed | 0.5 | 0.25 | 22 | Implement an XML format to create items
8 | Completed | 0.25 | 0.25 | 34 | Allow entities to hold an "infinite" number of items
9 | Completed | 0.5 | 0.5 | 35 | store number of item type { [1,Axe], [1,Arrow], [2,Sword] }
98 | Completed | 0 | 0.25 | - | Add Ability key to ability UI box
14 | Completed | 1 | 0.25 | 20 | Implement item stats that effect the entity if held
92 | In Progress | 1 | 0.5 | - | Creat UI button for menus
93 | In Progress | 1.5 | 0.5 | - | Create Game management of states MENU->PLAYING->LOSE->MENU
94 | In Progress | 1.5 | 0.5 | - | Create main menu
Date: | 2020-07-07 |  |  |  | Hours Worked: 5.5
92 | Completed | 1 | 0.5 | - | Creat UI button for menus
94 | Completed | 1.5 | 0.5 | - | Create main menu
24 | Completed | 1.5 | 2 | 3 | Create a menu that allows the player to choose 4 abilites from a catalog of abilities
86 | Completed | 1 | 1 | - | Add attack move cursor state
87 | Completed | 2 | 1.5 | - | Add player attack move state
Date: | 2020-07-12 |  |  |  | Hours Worked: 5 | Total Hours: 5
45 | Completed | 0.25 | 3 | 36 | Implement an entrance and exit functionality for the player to travel from floor to floor
2
Date: | 2020-07-13 |  |  |  | Hours Worked: 0 | Total Hours: 9

## Backlog
Task ID | Status | Estimate | Actual | Feature ID | Description
1 | Completed | 1.5 | 1.5 | 18 | Create Ability class
2 | Completed | 0.5 | 1.75 | 16 | Implement an XML format to create abilities
3 | Completed | 1 | 1 | 19 | Create Item class
4 | Completed | 0.5 | 0.25 | 22 | Implement an XML format to create items
5 | Completed | 0.75 | 0.75 | 18 | Create projectile class that is used by abilities
6 | Completed | 1.5 | 0.5 | 32 | Create entity class
7 | Completed | 0.25 | 0.25 | 33 | allow entities to hold up to 4 abilities
8 | Completed | 0.25 | 0.25 | 34 | Allow entities to hold an "infinite" number of items
9 | Completed | 0.5 | 0.5 | 35 | store number of item type { [1,Axe], [1,Arrow], [2,Sword] }
10 | Completed | 2.5 | 1.5 | 1 | Create a player character class that inherits entity class
11 | Completed | 1.5 | 0.5 | 2 | Implement ability to control player character via mouse
12 | Completed | 1 | 1 | 2 | Implement ability for player to use abilities
13 | Deleted | 1 |  | 7 | Implement dodge dash
14 | Completed | 1 | 0.25 | 20 | Implement item stats that effect the entity if held
15 | Deleted | 1 |  | 21 | Implement item actives
16 | Deleted | 1 |  | 21 | Implement the ability for the player to use equipped item actives
17 | Completed | 1 | 0.75 | 31 | Create an enemy class that inherits from entity
18 | Deleted | 2 |  | 8 | Create preset stat sets that modify the player character's base stats
19 | Deleted | 0.5 |  | 9 | Have stat sets hold experience
20 | Deleted | 0.5 |  | 9 | Assign number of skill points for stat set based on experience
21 | Deleted | 1 |  | 11,15 | Give each stat set a unique ability that utilizes its modified stats
22 | Deleted | 1.5 |  | 14 | Implement a way to updgrade abilities using the skill points from the selected stat set
23 | Deleted | 1 |  | 10 | Implement the ability to level up a stat set by assigning skill points
24 | Completed | 1.5 | 2 | 3 | Create a menu that allows the player to choose 4 abilites from a catalog of abilities
25 | Deleted | 0.5 |  | 4 | Create a menu that allows the player to choose which stat set they want to use
26 | Deleted | 0.5 |  | 4 | Display player stats with current loadout
27 | Deleted | 1 |  | 5 | Create a menu to assign skill points to abilities and/or stats
28 | Completed | 0.5 | 0.75 | 45 | Create an in game player health bar UI element
29 | Completed | 0.5 | 0.25 | 48 | Create an in game enemy health bar UI element
30 | Completed | 1 | 0.75 | 46 | Create an in game ability bar Ui that shows cooldowns for all equipped abilities
31 | Deleted | 2 |  | 6 | Create an in game Item inventory UI to select which items are in the active slots
32 | Deleted | 0.75 |  | 47 | Create an in game Item UI to show item active cooldowns
33 | Not Started | 1 |  | 29 | Create quick ranged weak enemy type
34 | Not Started | 1 |  | 29 | Create slow ranged strong enemy type
35 | Not Started | 1 |  | 29 | Create quick melee weak enemy type
36 | Not Started | 1 |  | 29 | Create slow melee strong enemy type
37 | Not Started | 1.5 |  | 30 | Implement simple AI for enemy to move and attack the player
38 | Deleted | 2 |  | 23 | Implement tile based room generation
39 | Completed | 2 | 1.5 | 24 | Implement room generation based on png files
40 | Deleted | 1.5 |  | 25 | Generate floors from randomly selected rooms connected via generated hallways
41 | Deleted | 0.5 |  | 26 | Ensure that each floor has an entrance room that doesnt have enemies
42 | Deleted | 0.5 |  | 28 | Ensure that each floor has an exit room free of enemies
43 | Deleted | 1 |  | 38 | he exit room will have 3 items that the player can choose from before progressing
44 | Not Started | 1 |  | 38 | Implement the ability for the player to pick up items by running over them
45 | Completed | 1 | 3.75 | 36 | Implement an entrance and exit functionality for the player to travel from floor to floor
46 | Not Started | 1 |  | 36 | Implement functionality for the player to return to the main menu upon losing all of their health
47 | Not Started | 1 |  | 39 | Increase enemy stats for every level
48 | Deleted | 1 |  | 40 | Increase number of enemies per room every 10 levels
49 | Deleted | 2 |  | 41 | Increase number of rooms per floor every 5 levels
50 | Deleted | 2 |  | 13 | Every 10 levels the player will unlock a new ability from a tier based system (tier = level/10)
51 | Not Started | 1.5 |  | 37 | Write save state to XML (save unlocked abilities and stat set EXP)
52 | Not Started | 1 |  | 37 | Read game save state from XML
53 | Not Started | 2 |  | - | Implement enemies that use abilities
54 | Not Started | 10 |  | - | Polish
55 | Not Started | 10 |  | - | Bug Fixing
Added Milestone 1
56 | Completed | 1 | 2 | 3, 16 | Implement Blink Ability type
57 | Completed | 1 | 1 | 3, 16 | Implement Buff Ability type
58 | Not Started | 1 |  | 3, 16 | Implement Projectile Ability type
59 | Not Started | 1 |  | 3, 16 | Implement targeted ability type
60 | Completed | 1 | 1 |  | Give the player the ability to attack the enemies (basic attack)
61 | Completed | 1.5 | 2 | 16 | Create a method to create abilities from definitions
62 | Completed | 1 | 1 | - | Sprint 2 Planning
63 | Completed | 1 | 1 | - | Reevaluate Milestones and Features
Added Milestone 2
64 | Completed | 1 | 0.5 | - | Explore posibilities of vector art
65 | Completed | 1 | 1.5 | - | Explore posibilities of using sprite art
66 | Completed | 1 | 2 | - | Get sprites to use in game
67 | Completed | 0.5 | 0.5 | - | Create World class to manage maps
68 | Completed | 0.5 | 0.5 | - | Create Map Class to hold tiled map
69 | Completed | 0.5 | 0.5 | - | Create tile struct to hold tile definitions
70 | Completed | 1 | 0.75 | - | Create tile definitions read in from XML
71 | Completed | 0.5 | 0.25 | - | Update game management to to World->Map->Entites
72 | Completed | 0.75 | 0.75 | - | Draw Tiles on screen with test texture
73 | Completed | 0.75 | 0.5 | - | Draw Tiles on screen with tile def textures
74 | Completed | 0.25 | 0.25 | - | Create a debugDraw button
75 | Completed | 0 | 0.75 | - | Debug existing SpriteSheet class
76 | Deleted | 2 | 0 | - | Add Simple Physics to map to not allow player to move through solid tiles
77 | Completed | 0 | 0.5 | - | Create Cursor SpriteSheet
78 | Completed | 0.5 | 0.5 | - | Update cursor logic to exist withing a Cursor class
79 | Completed | 0.5 | 0.25 | - | Add different states to cursor
80 | Completed | 0.5 | 0.5 | - | Update Cursor logic to allow easier modification
81 | Completed | 0.5 | 0.5 | - | Update Player logic to allow for easier modification
82 | Completed | 2 | 1 | - | Update entities to render sprites
83 | Completed | 0 | 1.5 | - | Animate Player actions
84 | Completed | 0 | 1 | - | Find an effective way to use external sprite sheets not in out typical format
85 | Completed | 0 | 0.25 | - | Realign Ability boxes and text
86 | Completed | 1 | 1 | - | Add attack move cursor state
87 | Completed | 2 | 1.5 | - | Add player attack move state
88 | Not Started | 1.5 |  | - | Add a raycast for line of sight logic
89 | Not Started | 3 |  | - | Add Map::PathFromLocationToPoint
90 | Not Started | 2 |  | - | Get Audio assets for: BGM, PlayerAttack, EnemyAttack, pick up Item
91 | Not Started | 1.5 |  | - | Implement playing audio on actions
92 | Completed | 1 | 1 | - | Creat UI button for menus
93 | In Progress | 1.5 | 0.5 | - | Create Game management of states MENU->PLAYING->LOSE->MENU
94 | Completed | 1.5 | 1 | - | Create main menu
95 | Not Started | 1.5 |  | - | Create pause menu
96 | Not Started | 1 |  | - | Add SFX volume control to menus
97 | Not Started | 1 |  | - | Add BGM volume control to menus
Added Milestone 3
98 | Completed | 0 | 0.25 | - | Add Ability key to ability UI box
Totals
|  | Estimated Hours | 92
|  | Actual Hours | 47.75